## Sheet1
A | Creating a plan
B | Researching Traffic signals and cameras
C | Deciding the programming langauge
D | Distributing roles to all members of the team
E | Designing a basic vehicle detection software (Version 1)
F | Testing V1
G | Debugging V1
H | Building the software with advanced vehicle detection as well as timer (V2)
J | Testing V2
I | Finding Bugs and Fixes
K | Final product done
L | Building V2
M | Testing the final product
Task | Time | Dependency
A | 3
B | 2 | A
C | 2 | B
D | 1 | C
E | 7 | D
F | 3 | E
G | 2 | F
H | 4 | G
J | 2 | H,M
I | 3 | I
K | 1 | J
L | 4 | E
M | 4 | L

## Sheet2
A | 3
0 |  | 3
0 |  | 3
3 | 0